## QA
Key | Description | Value (NOTE: cannot contain new-line chars) | Template | Sequence
ChangeTicketNum | Change ticket number | CHG0034013
ReleaseOwner | Change owner | Tom Lux
SprintsIncluded | Sprint numbers covered | 131 - 132
TargetEnv | Target environment | QA
TargetEnvShort |  | QA
DeployDate | Deploy date | 2018-12-11
ReleaseYear |  | 2019
ReleaseId |  | 1
IrmaClientUpdated |  | y
IrmaDbUpdated |  | y
IrmaLegacyUpdated |  | n
IconJobUpdated |  | y
IconDbUpdated |  | y
MammothJobUpdated |  | y
MammothDbUpdated |  | y
TibcoUpdated |  | y
FullSvrList | Servers receiving updates | .
ReleaseNotesURL | Link to release notes | .
IconDbScriptLink | Icon DB script | N/A -- Auto deploy via VSTS | <a href="file://irmaqafile/e$/IRMA/Staging/iCon/__IconVer__/DB/Icon%20__IconVer__%20Updates.sql">Icon __IconVer__ DB Updates</a>
MammothDbScriptLink |  | N/A -- Auto deploy via VSTS
MammothDbTarget |  | Mammoth-DB01-QA\Mammoth.Mammoth, QA-01-Mammoth02\Mammoth02.Mammoth | QA-01-Mammoth02\Mammoth02.Mammoth (Other QA DB is auto-deploy via VSTS)
IconReleaseBranchName | Icon release branch name | RELEASE_2019_1 | RELEASE_2018_12_Sprints129-130
IconBuildNum | Icon release build number | 20181210.1
IconBuildId | Icon release build ID | .
IrmaReleaseBranchName | IRMA release branch name | RELEASE_2019_1
IrmaBuildNum | IRMA release build number | 20181206.1
IrmaBuildId | IRMA release build ID | .
IrmaVer | IRMA version number | 10.7.1
IrmaLongVer |  | 10.7.1
IconVer | Icon version number | 9.9.1
MammothVer | Mammoth version number | 3.8.1
TibcoVer | TIBCO version number | 2.0.1
FullDbList | List of DBs receiving updates? | .
IrmaDbUpdateRegionList |  | FL, MA, MW, NA, NC, NE, PN, RM, SO, SP, SW, UK
IrmaDbServer |  | IDQ-xx\xxQ
IconDbServer |  | IDQ-Icon\SqlShared3Q
MammothDbServer |  | Mammoth-DB01-QA\Mammoth
AppSuitesBeingDeployed | This should be dynamic | IRMA, Icon, Mammoth, TIBCO
IrmaServersAffected | This should be dynamic | IRMAQAApp[1-4]
IconServersAffected | This should be dynamic | VM-Icon-QA[1-4]
MammothServersAffected | This should be dynamic | Mammoth-App01-QA
TibcoServersAffected | This should be dynamic | QA: CERD1673, CERD1674 ¦ QA-Perf: CERD1662, CERD1663, CERD1664, CERD1665 | QA: CERD1673, CERD1674 ¦ QA-Perf: CERD1662, CERD1663, CERD1664, CERD1665
TibcoAppsUpdated |  | MammothPriceListener,R10PriceService | # Valid app-list input: ActivePriceArchiver EmergencyPriceService ErrorMessagesListener ErrorMessagesMonitor ExpiringTprService IrmaPriceListener JobSchedulerService LoggingService MammothActivePriceService MammothPriceListener PriceListenerMessageArchiver PrimeAffinityListener R10PriceService
IrmaClientRollbackSteps |  | If limited or no user downloads, deploy previous version of IRMA Client via VSTS (anyone who downloaded new client, must remove 'apps\2.0\' folder). If many users downloaded client update, the version should be incremented in Git, then client rebuilt and deployed.
IrmaSuitePreviousVersion |  | 10.7.0
MammothManualDeploy |  | Manually deploy updated apps to Perf instances on Mammoth job server
IrmaReleaseLauncherVersionRef |  | .
AdditionalIrmaComponentDeploySection | Usually a link to a component-deploy script, such as "IRMA Release Launcher" powershell | Using release branch as source, manually upload reports into <a href="http://irmaqarpt/Reports/Pages/Folder.aspx?ItemPath=%2fIcon&ViewMode=Detail">IIS QA Icon Folder</a>: Icon IRMA Sign Attributes Comparison.rdl, IconItemSearch.rdl | Open folder <a href="\\irmaqafile\e$\irma\Staging\Release\Launcher">Release Launcher Folder</a>. Right-click script "IRMA Release Launcher.__IrmaReleaseLauncherVersionRef__.%env%.ps1" > Run with PowerShell…
AdditionalIrmaDeployImplementerRef |  | IRM |  |  | AdditionalIrmaComponentDeploySection
AdditionalIrmaComponentList |  | *NONE*
SpecialIrmaReleaseDetails |  | <hr>
SpecialIconReleaseDetails |  | <hr>
IrmaPostDbUpdateTask |  | None, continue

## Prod
Key | Description | Value (NOTE: cannot contain new-line chars) | Template | Sequence | Special Task
ChangeTicketNum | Change ticket number | CHG0034401
ReleaseOwner | Change owner | Tom Lux
SprintsIncluded | Sprint numbers covered | 129-132
TargetEnv | Target environment | Production
TargetEnvShort |  | PRD
DeployDate | Deploy date | 2019-01-17
ReleaseYear |  | 2019
ReleaseId |  | 1
IrmaClientUpdated |  | y
IrmaDbUpdated |  | y
IrmaLegacyUpdated |  | y
IconJobUpdated |  | y
IconDbUpdated |  | y
MammothJobUpdated |  | y
MammothDbUpdated |  | y
TibcoUpdated |  | y
FullSvrList | Servers receiving updates | .
ReleaseNotesURL | Link to release notes | .
MammothDbTarget |  | Mammoth-DB01-Prd\Mammoth
IconReleaseBranchName | Icon release branch name | RELEASE_2019_01
IconBuildNum | Icon release build number | 20190110.1
IconBuildId | Icon release build ID
IrmaReleaseBranchName | IRMA release branch name | RELEASE_IRMA106_Sprints127-128
IrmaBuildNum | IRMA release build number | 20190110.1
IrmaBuildId | IRMA release build ID
IrmaVer | IRMA version number | 10.7
IrmaLongVer |  | 10.7.0
IconVer | Icon version number | 9.9
MammothVer | Mammoth version number | 3.8
TibcoVer | TIBCO version number | 2.0
FullDbList | List of DBs receiving updates? | .
IconDbScriptLink | Icon DB script | <a href="file://irmaqafile/e$/IRMA/Staging/iCon/__IconVer__/DB/Icon%20__IconVer__%20Updates.sql">Icon __IconVer__ DB Updates</a> | <a href="file://irmaqafile/e$/IRMA/Staging/iCon/__IconVer__/DB/Icon%20__IconVer__%20Updates.sql">Icon __IconVer__ DB Updates</a> | N/A -- Auto deploy via VSTS
MammothDbScriptLink |  | <a href="file://irmaqafile/e$/IRMA/Staging/mammoth/__MammothVer__/DB/Mammoth%20__MammothVer__%20Updates.sql">Mammoth __MammothVer__ DB Updates</a>
IrmaDbUpdateRegionList |  | FL, MA, MW, NA, NC, NE, PN, RM, SO, SP, SW, UK
IrmaDbServer |  | IDP-xx\xxP
IconDbServer |  | IDP-Icon\Shared3P
MammothDbServer |  | Mammoth-DB01-Prd\Mammoth
AppSuitesBeingDeployed | This should be dynamic | IRMA, Icon, Mammoth, TIBCO
IrmaServersAffected | This should be dynamic | IRMAPrdApp[1-8]
IconServersAffected | This should be dynamic | VM-Icon-Prd[1-6]
MammothServersAffected | This should be dynamic | Mammoth-App01-QA, IRMAPrdApp[9-10]
TibcoServersAffected | This should be dynamic | Prod: cerp1643, cerp1644, odrp1634, odrp1635 | QA: CERD1673, CERD1674 ¦ QA-Perf: CERD1662, CERD1663, CERD1664, CERD1665 Prod: cerp1643, cerp1644, odrp1634, odrp1635
TibcoAppsUpdated |  | MammothPriceListener,R10PriceService,PublishInventorySpoilageService,PublishPurchaseOrderService,PublishReceivedOrderService,PublishTransferOrderService,RePublishInventoryMessagesService
IrmaClientRollbackSteps |  | If limited or no user downloads, deploy previous version of IRMA Client via VSTS (anyone who downloaded new client, must remove 'apps\2.0\' folder). If many users downloaded client update, the version should be incremented in Git, then client rebuilt and deployed.
IrmaSuitePreviousVersion |  | 10.6.0
MammothManualDeploy |  | *NONE* | After main Mammoth VSTS release, run release: 'RELEASE_FastTrack_Sprints127-128' branch, deploy: Mammoth Web Support
IrmaReleaseLauncherVersionRef |  | .
AdditionalIrmaDeployImplementerRef |  | IRMA DevOps, DBA
AdditionalIrmaComponentDeploySection | Usually a link to a component-deploy script, such as "IRMA Release Launcher" powershell | [1 of 2] (IRMA DevOps) Using release branch as source, manually upload report into <a href="http://irmaprdrpt/Reports/Pages/Folder.aspx?ItemPath=%2fIcon&ViewMode=Detail">IIS Prd Icon Folder</a>: IconItemSearch.rdl<BR>[2 of 2] (DBA, IRMA DevOps) Open and implement <a href="http://sites/global/ChangeControlDocumentation/Change%20Control%20Documentation/HoneyCrisp%20Prd%20-%20Setup%20ItemVendorLane%20SSIS%20Pkgs.docx">HoneyCrisp Prod Setup ItemVendorLane SSIS</a>.<BR>__AdditionalIrmaComponentList__ | Open folder <a href="\\irmaqafile\e$\irma\Staging\Release\Launcher">Release Launcher Folder</a>. Right-click script "IRMA Release Launcher.__IrmaReleaseLauncherVersionRef__.__TargetEnvShort__.ps1" > Run with PowerShell<br>__AdditionalIrmaComponentList__
AdditionalIrmaComponentList |  | **Component Summary**: 'Icon Item Search' SSRS Report, HoneyCrisp SSIS Setup
SpecialIrmaReleaseDetails |  | <hr>
SpecialIconReleaseDetails |  | <hr> | <hr>Additional special-fixes build, 'RELEASE_FastTrack_Sprints127-128' branch, build=20181030.1
IrmaPostDbUpdateTask |  | None, continue | <span style='background:lime;mso-highlight:lime'>**Start Price-Batch Purge ASAP** (see separate doc)</span> |  | x

## other ideas
Each need to be included in pre-deploy ‘mark offline for maint’
IRMA Client being deployed?
IRMA legacy apps being deployed?
Link to launcher script built from IRMA version number
Special steps needed for certain legacy apps
IRMA DB script
Mammoth DB script
TIBCO app list
Link to TIBCO deploy framework docs
Post-deploy DB ‘mark open for biz’